## Test cases
Req ID | Req Name | Test Scenario ID | Test Scenario Name | Test case ID | Test case | Test steps | Test data | Expected outcome | Actual outcome | Step Status | Defect ID | Defect description
Req 01 | Zomato App Launch | Req 01_TS01 | User launches zomato app | Req 01_TS01_TC01 | Check whether user is able to launch zomato app | 1.User selects the zomato app 2.App navigates to sign up page automatically | Android Apps by Zomato on Google Play | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number | 1.Zomato app launched successfully 2.App is automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number | 1.Pass 2.Pass
Req 02 | Register module | Req 02_TS02 | User registration | Req 02_TS02_TC02.1 | Check whether new user is able to register with valid data | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically | Country code: +91 Mobile: 9398147994 | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the valid mobile number 5.User should receive an OTP in user mobile number | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Valid mobile number is entered in the text field box 5.A valid otp is generated in the user mobile number | 1.Pass 2.Pass 3.Pass 4.Pass 5.Pass
|  |  |  | Req 02_TS02_TC02.2 | Check whether new user is able to register with invalid data | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically | Country code: +91 Mobile: 9398147 | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the invalid mobile number 5.User should not receive an OTP in user mobile number | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Invalid mobile number is entered in the text field box 5."Otp is generated in the user mobile number" message is displayed. | 1.Pass 2.Pass 3.Pass 4.Pass 5.Fail | Req 02_TS02_TC2.2_TS05_DEF01 | Invalid phone number accepted during registration/sign up
|  |  |  | Req 02_TS02_TC2.3 | Check whether existing user is able to register | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the registered mobile number in the text field box 5.An otp generates automatically | Country code: +91 Mobile: 9398147994 | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the registered mobile number 5.User should receive "Already existing user,please try to login" message | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Registered mobile number is entered in the text field box 5.Otp is generated in the user mobile number | 1.Pass 2.Pass 3.Pass 4.Pass 5.Fail | Req 02_TS02_TC2.3_TS05_DEF02 | Already registered user is able to register again
Req 03 | Login Module | Req 03_TS03 | User login using google account | Req 03_TS03_TC03.2 | Check whether user is able to login using google account | 1.User selects the zomato app 2.App navigates to sign up page automatically and taps on google icon 3.User selects the google account from dialoge box 4.User credentials are verified automatically and navigates to home page | Google account: Srihithareddykarnati@gmail.com | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a google icon should appear for user to select 3.Google account should be selected from the dialoge box by the user 4.User credentials should be verified automatically and navigate to home page | 1.Zomato app launched successfully 2.App navigated to sign up page,a google icon appeared for user to select 3.Google account is selected from the dialoge box by the user 4.User credentials are verified automatically and navigated to home page | 1.Pass 2.Pass 3.Pass 4.Pass
|  | Req 03_TS04 | User login using email account | Req 03_TS05_TC05 | Check whether user is able to login using email | 1.User selects the zomato app 2.App navigates to sign up page automatically and taps on email icon 3.User enters the email in the text field box 4.An otp generates automatically 5.User enters the otp in th text field box which is received to email 6.User clicks on login and navigates to home page | Email: Srihithareddykarnati@gmail.com OTP: 456789 | 1. Zomato app should be launched successfully 2.App should be navigated to sign up page automatically and email icon should be selected 3.User should enter the email in the text field box 4.An otp should be generated automatically to users's mail 5.User should enter the otp in th text field box which is received to email 6.User should click on login and it should be navigated to home page | 1. Zomato app launched successfully 2.App is navigated to sign up page automatically and email icon is selected 3.User entered the email in the text field box 4.An otp is generated automatically to users's mail 5.User entered the otp in th text field box which is received to email 6.User clicked on login and it is navigated to home page | 1.Pass 2.Pass 3.Pass 4.Pass 5.Pass 6.Pass
Req 04 | Order module | Req 03_TS05 | User searches food items | Req 03_TS05_TC06 | Check whether user is able to search food item | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically 6.User clicks on login automatically it navigates to home page 7.User enters the food item in the search bar 8.A list of restaurent names appears to the user | Country code: +91 Mobile : 9398147994 OTP: 564000 search: biryani | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the valid mobile number 5.User should receive an OTP in user mobile number 6.User should login and navigated to home page 7.User should enter the food item name in the search field 8.User should be able to see the list of restaurents | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Valid mobile number is entered in the text field box 5.A valid otp is generated in the user mobile number 6.User is logged in and automatically navigated to home page 7.User entered the food item name in the search field 8.User is able to see the list of restaurent names | 1.Pass 2.Pass 3.Pass 4.Pass 5.Pass 6.Pass 7.Pass 8.Pass
|  | Req 03_TS06 | User adds food items to the cart | Req 03_TS06_TC07 | Check whether user is able to add food items to the cart | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically 6.User clicks on login automatically it navigates to home page 7.User enters the food item in the search bar 8.A list of restaurent names appears to the user 9.User selects a restaurent and selects the food item 10.User adds the required quantity of that food item to cart | Country code : +91 Mobile : 9398147994 OTP: 564000 search: biryani Restaurent name: Mehfill Qty:1 | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the valid mobile number 5.User should receive an OTP in user mobile number 6.User should login and navigated to home page 7.User should enter the food item name in the search field 8.User should be able to see the list of restaurents 9.User should select restaurent and the food item 10.User should add the food item to the cart in required quantity | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Valid mobile number is entered in the text field box 5.A valid otp is generated in the user mobile number 6.User is logged in and automatically navigated to home page 7.User entered the food item name in the search field 8.User is able to see the list of restaurent names 9.User selected the restaurent and the food item 10.User added the food item to the cart in required quantity | 1.Pass 2.Pass 3.Pass 4.Pass 5.Pass 6.Pass 7.Pass 8.Pass 9.Pass 10.Pass
|  | Req 03_TS07 | User adds the address and completes the payment | Req 03_TS07_TC08 | Check whether user is able to add the address and complete the payment | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically 6.User clicks on login automatically it navigates to home page 7.User enters the food item in the search bar 8.A list of restaurent names appears to the user 9.User selects a restaurent and selects the food item 10.User adds the required quantity of that food item to cart 11.User clicks on view cart 12.User need to add the address to place order , so user adds the address in the address field (House number,Locality/area,CIty,State,pincode,country) 13.User selects the payment method (UPI/Card/COD/Net Banking) 14.User enters the required credentials (for upi,user enters upi id in the text field) and completes the payment | Country code: +91 Mobile : 9398147994 OTP: 564000 search: biryani Restaurent name: Mehfill Qty:1 Address: Ishtaa blooms girls hostel,narsingi,Hyderabad,Telangana,500075,India. Payment method: upi Upi id:srihithareddykarnati@oksbi | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the valid mobile number 5.User should receive an OTP in user mobile number 6.User should login and navigated to home page 7.User should enter the food item name in the search field 8.User should be able to see the list of restaurents 9. Restaurent and the food item should be selected 10.Food item should be added to the cart in required quantity 11.Address should be saved and selected 12.User should be navigated to payment page 13.Payment method selected by the user(UPI/Card/COD/Net banking) should be displayed. 14.Payment should be completed successfully and order should be placed | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Valid mobile number is entered in the text field box 5.A valid otp is generated in the user mobile number 6.User is logged in and automatically navigated to home page 7.User entered the food item name in the search field 8.User is able to see the list of restaurent names 9.User selected the restaurent and the food item 10.User added the food item to the cart in required quantity 11.11.Address is saved and selected 12.User navigated to payment page 13.Payment method selected by the user(UPI/Card/COD/Net banking) is displayed. 14.Payment is failed and order is not placed. | 1.Pass 2.Pass 3.Pass 4.Pass 5.Pass 6.Pass 7.Pass 8.Pass 9.Pass 10.Pass 11.Pass 12.Pass 13.Pass 14.Fail | Req 03_TS07_TC08_TS14_DEF03 | Payment gateway error

## Bug report
Defect ID | Summary | Steps to reproduce | Expected result | Actual result | Severity | Priority | Status
Req 02_TS02_TC2.2_TS05_DEF01 | Invalid phone number is accepted during sign up in zomato app | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the invalid mobile number 5.User should not receive an OTP in user mobile number | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Invalid mobile number is entered in the text field box 5."Otp is generated in the user mobile number" message is generated | High | High | New
Req 02_TS02_TC2.3_TS05_DEF02 | Already registered user is able to register again | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the registered mobile number in the text field box 5.An otp generates automatically | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the registered mobile number 5.User should receive "Already existing user,please try to login" message | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Registered mobile number is entered in the text field box 5.Otp is generated in the user mobile number | High | High | New
Req 03_TS07_TC08_TS14_DEF03 | Payment fails even with valid upi id | 1.User selects the zomato app 2.App navigates to sign up page automatically 3.User enters the country code from dropdown in the dialoge box 4.User enters the mobile number in the text field box 5.An otp generates automatically 6.User clicks on login automatically it navigates to home page 7.User enters the food item in the search bar 8.A list of restaurent names appears to the user 9.User selects a restaurent and selects the food item 10.User adds the required quantity of that food item to cart 11.User clicks on view cart 12.User need to add the address to place order , so user adds the address in the address field (House number,Locality/area,CIty,State,pincode,country) 13.User selects the payment method (UPI/Card/COD/Net Banking) 14.User enters the required credentials (for upi,user enters upi id in the text field) and completes the payment | 1.Zomato app should be launched successfully 2.App should navigate to sign up page,a prompt dialoge box should appear for user's mobile number 3.Country code should be selected in the dialoge box,, a flag should appear corresponding to the country code 4.User should enter the valid mobile number 5.User should receive an OTP in user mobile number 6.User should login and navigated to home page 7.User should enter the food item name in the search field 8.User should be able to see the list of restaurents 9. Restaurent and the food item should be selected 10.Food item should be added to the cart in required quantity 11.Address should be saved and selected 12.User should be navigated to payment page 13.Payment method selected by the user(UPI/Card/COD/Net banking) should be displayed. 14.Payment should be completed successfully and order should be placed | 1.Zomato app launched successfully 2.App automatically navigated to sign up page,a prompt dialoge box appeared for user's mobile number 3.Country code is selected in the dialoge box,, a flag appeared corresponding to the country code 4.Valid mobile number is entered in the text field box 5.A valid otp is generated in the user mobile number 6.User is logged in and automatically navigated to home page 7.User entered the food item name in the search field 8.User is able to see the list of restaurent names 9.User selected the restaurent and the food item 10.User added the food item to the cart in required quantity 11.11.Address is saved and selected 12.User navigated to payment page 13.Payment method selected by the user(UPI/Card/COD/Net banking) is displayed. 14.Payment is failed and order is not placed. | Critical | HIgh | New

## Test closure report
Executive Summary 1.Test execution completed for zomato app with 66.67% pass rate 2.3 new defects were identified which affect sign up,order module 3.Failures are critical to business functionality 4.App is not production ready until defects are fixed and closed
Test execution report | [8 empty] | Defect status
Functionality | Test cases | Pass | Fail | No Run | Blocked | Execution % | Pass % | Fail% | Status | P1(critical) | P2(High) | P3(Medium) | P4(Low) | Total
App Launch | 1 | 1 | 0 | 0 | 0 | 100 | 100 | 0 | New | 1 | 2 | 0 | 0 | 3
Sign up/register | 3 | 1 | 2 | 0 | 0 | 100 | 33.33 | 66.67 | Assigned | 0 | 0 | 0 | 0 | 0
Login | 2 | 2 | 0 | 0 | 0 | 100 | 100 | 0 | Open | 0 | 0 | 0 | 0 | 0
Food ordering | 3 | 2 | 1 | 0 | 0 | 100 | 66.67 | 33.33 | Fixed | 0 | 0 | 0 | 0 | 0
Total | 9 | 6 | 3 | 0 | 0 | 100 | 66.67 | 33.33 | Retest | 0 | 0 | 0 | 0 | 0
[9 empty] | Closed | 0 | 0 | 0 | 0 | 0
[9 empty] | Rejected | 0 | 0 | 0 | 0 | 0
[9 empty] | Deferred | 0 | 0 | 0 | 0 | 0
[9 empty] | Duplicate | 0 | 0 | 0 | 0 | 0
[9 empty] | Total | 1 | 2 | 0 | 0 | 3
Change request status table
| Status | High | Medium | Low | Total
| New | 0 | 0 | 0 | 0
| In review | 0 | 0 | 0 | 0
| Approved | 0 | 0 | 0 | 0
| Rejected | 0 | 0 | 0 | 0
| Total | 0 | 0 | 0 | 0